## Sheet1
Date | Topic | Update | Sentiment
2017-08-15 | Data | Inception wrapping up this week | Positive
2017-08-15 | Data | two developers starting today | Positive
2017-08-15 | Data | Solution and Architecture blueprints in progress; meeting with Stakeholders on Tues | Neutral
2017-08-15 | Data | Backlog in progress | Neutral
2017-08-15 | Data | Complete data source matrix | Neutral
2017-08-15 | Algorithms | Planning meeting last Friday | Neutral
2017-08-15 | Algorithms | Sprint started today | Positive
2017-08-15 | Algorithms | TFS structure set up | Positive
2017-08-15 | Testing | Meeting scheduled for Tuesday with stakeholders | Neutral
2017-08-15 | Testing | Test users don’t have access to Data Lake for ingestion testing | Negative
2017-08-15 | Testing | Delayed preparation of data to be used for development & testing until integration is available | Negative
2017-08-15 | UI | Deployment to development servers complete | Positive
2017-08-15 | UI | Troubleshooting some functionality issues reported by tester | Negative
2017-08-31 | Data | Inception wrapping up this week – Environment config | Positive
2017-08-31 | Data | Environment requested – to be completed on Monday | Positive
2017-08-31 | Data | Confirm with Tech Arch the mechanism needed to ingest conversion data to DL | Neutral
2017-08-31 | Data | Backlog in progress for Sprint 1 (4 stories - POC ingestions & formatting) | Positive
2017-08-31 | Data | Complete data source matrix - tables & names (dependency on data source teams) | Neutral
2017-08-31 | Data | Reviewing sources, in particular Demand data to evaluate possibility of using it in conversion | Neutral
2017-08-31 | Data | Employee data obtained from Demand; no Industry skill present | Negative
2017-08-31 | Algorithms | New sandbox is configured | Positive
2017-08-31 | Algorithms | Met with Test team – test environment ready and data has been migrated | Positive
2017-08-31 | Algorithms | Work with Test Lead and Scrum Master to resolve access issues for test users | Negative
2017-08-31 | UI | Sprint 4 to wrap up on Wed Aug 2 - final testing Tuesday | Neutral
2017-08-31 | UI | Critical defect to be resolved before Wednesday | Negative
2017-08-31 | UI | Sprint 5 stories identified – choose on Wed call after demo | Neutral
2017-08-31 | UI | Admin stories – begin discussing for Sprint 6 | Neutral
2017-08-31 | Testing | UI test cases added in TFS; under review with customer | Positive
2017-08-31 | Testing | Updating TFS dashboard | Neutral
2017-08-31 | Testing | Preparing input/output data | Positive
2017-08-31 | Testing | Still need to resolve test user access issues for ingestion testing | Negative
2017-08-31 | Testing | Daily call with data team to prep test conditions | Positive